## Overview
M-Kristo App — Tracker
Client: Baraka ¦ Developer: Philip Steven Chediel, BlueGrid Technologies
Generated on | 2026-08-14
Total tasks | 21
Done | 2
In progress | 1
Overall progress | 10%
Total project cost | 3,500,000 TZS
Paid so far | 0 TZS
Remaining | 3,500,000 TZS
Task status breakdown
Done | 2
Not Started | 18
In Progress | 1

## Progress Tracker
M-Kristo App — Progress Tracker
Update this via tracker_data.py and rerun generate_tracker.py
Phase | Task | Owner | Status | % Complete | Start Date | Due Date | Notes
1. Setup & Design | Project structure & repo setup | Philip Steven Chediel | Done | 100% | 2026-08-14 | 2026-08-14 | architecture/, guide.md, progress.md created.
1. Setup & Design | PostgreSQL database schema design | Philip Steven Chediel | Done | 100% | 2026-08-14 | 2026-08-16 | architecture/database_schema.sql + DATABASE_SCHEMA.md.
1. Setup & Design | UI/UX design (screens & flows) | Philip Steven Chediel | Not Started | 0%
2. Core Build | Django project & app scaffolding | Philip Steven Chediel | In Progress | 10% | 2026-08-14
2. Core Build | Auth: signup/login + phone OTP | Philip Steven Chediel | Not Started | 0%
2. Core Build | Social login (Google/Apple) | Philip Steven Chediel | Not Started | 0%
2. Core Build | Bible module (Swahili + English) | Philip Steven Chediel | Not Started | 0%
2. Core Build | Daily content: Neno la Leo, Tafakari, Somo | Philip Steven Chediel | Not Started | 0%
2. Core Build | Sala (common prayers) | Philip Steven Chediel | Not Started | 0%
2. Core Build | Dictionary (biblical term lookup/translation) | Philip Steven Chediel | Not Started | 0%
2. Core Build | Notes & calendar (Shajara) | Philip Steven Chediel | Not Started | 0%
2. Core Build | Favorites | Philip Steven Chediel | Not Started | 0%
3. Premium & Subscriptions | Novena (premium) | Philip Steven Chediel | Not Started | 0%
3. Premium & Subscriptions | Tenzi / hymns (premium) | Philip Steven Chediel | Not Started | 0%
3. Premium & Subscriptions | Subscription plans & premium gating | Philip Steven Chediel | Not Started | 0%
4. Notifications & Sharing | Push notifications (FCM/EAS) | Philip Steven Chediel | Not Started | 0%
4. Notifications & Sharing | Native sharing (Android/iOS) | Philip Steven Chediel | Not Started | 0%
5. Testing & Hosting | QA / testing pass | Philip Steven Chediel | Not Started | 0%
5. Testing & Hosting | Backend hosting & deployment | Philip Steven Chediel | Not Started | 0%
5. Testing & Hosting | App store preparation (Android/iOS) | Philip Steven Chediel | Not Started | 0%
5. Testing & Hosting | Source code & documentation handover | Philip Steven Chediel | Not Started | 0%

## Payment Summary
M-Kristo App — Payment Summary
Client: Baraka ¦ Total agreed cost: 3,500,000 TZS
Milestone | Description | Amount | Currency | Status | Due Date | Paid Date
1. Commencement | Payment to commence development, through to hosting. | 2500000 | TZS | Pending
2. Completion | Final payment on completion and handover. | 1000000 | TZS | Pending
TOTAL |  | 3500000
Paid so far | 0 TZS
Remaining | 3,500,000 TZS